## Product
Team 6
Thad Hogan (AI +Client Server)
Krista Capps (GM + Client-Server)
Anh Nguyen (GUI + PM)
Product Backlog | [5 empty] | Log Date | Ideal Remaining Hours | Remaining Hours
|  |  | Task | Hours | Sprint #1 | 2017-10-28 | 266 | 266
GUI | Game Display | 1 | Title/introduction screen/message | 5 |  | 2017-10-29 | 254.9 | 260
|  | 2 | Option for game menu#1 (Singleplayer/ Multiplayer) | 4 |  | 2017-10-30 | 243.8 | 245
|  | 3 | Option for game menu#2 (4/5/6 seeds) | 3 |  | 2017-10-31 | 232.7 | 230
|  | 4 | Layout of the current state of the board (12 round pits, 2 large oval pits) | 8 |  | 2017-11-01 | 221.6 | 222
|  | 5 | Display seeds in each pits | 4 |  | 2017-11-02 | 210.5 | 210
|  | 6 | Player scores | 2 |  | 2017-11-03 | 199.4 | 195
|  | 7 | Game result | 2 |  | 2017-11-04 | 188.3 | 195
|  | 8 | Invalid move | 1 | Sprint #2 | 2017-11-05 | 177.2 | 195
| Game Update | 9 | Receive user input for option in Menu screen by mouse click | 8 |  | 2017-11-06 | 166.1 | 173
|  | 10 | Receive user input for making move by mouse click | 8 |  | 2017-11-07 | 155 | 156
|  | 11 | Update game board after each move | 10 |  | 2017-11-08 | 143.9 | 134
|  | 12 | Update player score after each move | 6 |  | 2017-11-09 | 132.8 | 106
|  | 13 | Popup game results if the game is finished | 5 |  | 2017-11-10 | 121.7 | 88
|  | 14 | Popup invalid move | 4 |  | 2017-11-11 | 110.6 | 88
| Animation & Visual | 15 | Make animation for seeds when player make move | 7 | Sprint #3 | 2017-11-12 | 99.5 | 88
|  | 16 | Update visual | 3 |  | 2017-11-13 | 88.4 | 77
Game Manager | Board State | 17 | Set board | 10 |  | 2017-11-14 | 77.3 | 68
|  | 18 | Reset score | 2 |  | 2017-11-15 | 66.2 | 58
|  | 19 | Initialize values | 4 |  | 2017-11-16 | 55.1 | 43
|  | 20 | Save board state data | 10 |  | 2017-11-17 | 44 | 39
|  | 21 | Determine hole sides | 1 |  | 2017-11-18 | 32.9 | 25
|  | 22 | Determine New sums after move | 6 |  | 2017-11-19 | 21.8 | 17
|  | 23 | Determine point distribution | 15 |  | 2017-11-20 | 10.7
| Rule Checker | 24 | Handle captures | 8 |  | 2017-11-21 | 0
|  | 25 | Check valid move | 15
|  | 26 | Handle AI Calls | 20
|  | 27 | Handle GUI Interactions | 20
AI | Research | 28 | Become clear on the rules of mancala | 1
|  | 29 | Research best strategies for mancala | 3
| AI movement | 30 | AI can select a valid move at random | 2
|  | 31 | Develop a move simulator based off of the game manager | 4
|  | 32 | AI that can look ahead one move in tree | 5
| Min/Max Tree | 33 | Research minimax tree implementation | 2
|  | 34 | Create minimax tree | 5
| Alpha-Beta Pruning | 35 | Research Anpha-beta pruning | 2
|  | 36 | Alpha-beta pruning implemented at one level | 8
|  | 37 | Alpha-beta pruning implimented across all levels | 8
| Interative Deepening | 38 | Impliment iterative deepening | 8
Client-Server | Research | 39 | Research Client-server model | 2
|  | 40 | Find a java class to use for a remote client access | 3
|  | 41 | Become clear on use of the java class | 8
| Client Funtion of Networking | 42 | Plan out general client-server method for game | 4
|  | 43 | Impliment client-sever connection that does nothing | 6
|  | 44 | Impliment client-server connection that passes game data | 4
|  |  | Total Hours | 266

## Sprint#1
Sprint#1 Backlog |  |  |  | Log Date | Ideal Remaining Hours | Remaining Hours
|  | Task | Hours | 2017-10-28 | 71 | 71
GUI | 1 | Title/introduction screen/message | 5 | 2017-10-29 | 59.2 | 65
| 2 | Option for game menu#1 (Singleplayer/ Multiplayer) | 4 | 2017-10-30 | 47.4 | 50
| 3 | Option for game menu#2 (4/5/6 seeds) | 3 | 2017-10-31 | 35.6 | 35
| 4 | Layout of the current state of the board (12 round pits, 2 large oval pits) | 8 | 2017-11-01 | 23.8 | 27
| 5 | Display seeds in each pits | 4 | 2017-11-02 | 12 | 15
| 6 | Player scores | 2 | 2017-11-03 | 0 | 0
Game Manager | 7 | Set board | 10
| 8 | Reset score | 2
| 9 | Initialize values | 4
| 10 | Save board state data | 10
AI | 11 | Become clear on the rules of mancala | 1
| 12 | Research best strategies for mancala | 3
| 13 | AI can select a valid move at random | 2
Client-Server | 14 | Research Client-server model | 2
| 15 | Find a java class to use for a remote client access | 3
| 16 | Become clear on use of the java class | 8
|  | Total Hours | 71

## Sprint#2
Sprint#2 Backlog |  |  |  |  | Log Date | Ideal Remaining Hours | Remaining Hours
|  | Task | Hours | Remaining Hours | 2017-11-05 | 132 | 132
GUI | 1 | Receive user input for option in Menu screen by mouse click | 8 | 0 | 2017-11-06 | 105.6 | 110
| 2 | Receive user input for making move by mouse click | 8 | 0 | 2017-11-07 | 79.2 | 93
| 3 | Update game board after each move | 10 | 6 | 2017-11-08 | 52.8 | 71
| 4 | Update player score after each move | 6 | 6 | 2017-11-09 | 26.4 | 43
Game Manager | 6 | Check valid move | 15 | 0 | 2017-11-10 | 0 | 25
| 7 | Handle AI Calls | 20 | 0
| 8 | Handle GUI Interactions | 20 | 10
| 9 | Determine point distribution | 15 | 0
AI | 10 | Develop a move simulator based off of the game manager | 4 | 0
| 11 | Ai that can look ahead one move in tree | 5 | 0
| 12 | Research minimax tree implementation | 2 | 0
| 13 | Create minimax tree | 5 | 0
Client-Server | 14 | Plan out general client-server method for game | 4 | 0
| 15 | impliment client-sever connection that does nothing | 6 | 0
| 16 | impliment client-server connection that passes game data | 4 | 3
|  | Total Hours | 132 | 25

## Sprint#3
Sprint#3 Backlog |  |  |  | Log Date | Ideal Remaining Hours | Remaining Hours
|  | Task | Hours | 2017-11-12 | 88 | 88
GUI | 1 | Game result | 2 | 2017-11-13 | 78.2 | 77
| 2 | Invalid move | 1 | 2017-11-14 | 68.4 | 68
| 3 | Update game board after each move | 6 | 2017-11-15 | 58.6 | 58
| 4 | Update player score after each move | 6 | 2017-11-16 | 48.8 | 43
| 5 | Popup game results if the game is finished | 5 | 2017-11-17 | 39 | 39
| 6 | Popup invalid move | 4 | 2017-11-18 | 29.2 | 25
| 7 | Make animation for seeds when player make move | 7 | 2017-11-19 | 19.4 | 17
| 8 | Update visual | 3 | 2017-11-20 | 9.6
Game Manager | 9 | Determine hole sides | 1 | 2017-11-21 | 0
| 10 | Determine New sums after move | 6
| 11 | Handle GUI Interation (continue) | 10
| 12 | Handle captures | 8
AI | 13 | Research Anpha-beta pruning | 2
| 14 | Alpha-beta pruning implemented at one level | 8
| 15 | Alpha-beta pruning implimented across all levels | 8
| 16 | Impliment iterative deepening | 8
Client-Server | 17 | impliment client-server connection that passes game data (continue) | 3
|  | Total Hours | 88